NICKJEWELL.AI

Project Roadmap v3

Unified Build Plan  |  Three Parallel Workstreams  |  March 30, 2026

Companion document: NickJewellAI_Agentic_Operations_Architecture.docx (strategic blueprint)

# What’s Built & Deployed

Homepage with thesis, pattern section, framework preview, logo section, writing, contact. Framework page with 5-layer deep dive, company stories, transitions, sticky layer nav, assessment backlinks. Assessment engine with 3-tier adaptive flow, API integration (Sonnet 4 + Opus 4.6), streaming executive brief, contact form gate, deterministic fallback. 5 standalone writing pages with SEO and inline CTAs. Save Results email pipeline via Resend. nick@nickjewell.ai (send + receive). OG images for all 3 pages. Full accessibility overhaul (WCAG AA). SEO infrastructure (sitemap, robots, structured data, favicon). D1 auto-capturing all assessments with enriched Pulse fields. Admin bypass for rate limiting. www redirect. Framework sticky layer nav. About page deployed at /about/ (unlinked from nav). D1 read endpoint (/d1-read). CLAUDE.md and Project Status updated to current deployed state.

# Changelog from Roadmap v2

- B1 (About page): Moved to DONE. Deployed but intentionally unlinked from nav pending B2.

- B5 (D1 query endpoint): Scope expanded and renumbered as I1 (D1 REST API). Now includes POST, structured endpoints, and webhook dispatch. Effort increased from 30 min to 2–3 hrs. Serves both Workstream A (chat queries) and Workstream C (agent data access).

- D1 (Project Status update): Moved to DONE. Completed March 29.

- D2 (CLAUDE.md update): Moved to DONE. Completed March 29.

- L5 + L6 (Engagement packages): Pulled forward from Future to Workstream B as I6 dependency. Required for Layer 2 Engagement Matcher agent.

- New Workstream B (I1–I7): 7 data and intelligence infrastructure items added. These are the shared backbone that serves both the product and the agentic layer.

- New Workstream C (C1–C11): 11 agentic operations items across 3 capability layers. 4 scheduled workers, 4 single agents, 1 orchestrated pipeline, plus Python runtime and integration testing.

- Build sequence: Replaced sequential phases with simultaneous parallel workstreams across 12 sessions.

# All Open Items (35 total across 3 workstreams)

## Workstream A: Product & Content (15 items)

The assessment product, site features, testing, content publishing. Scope carried from Roadmap v2 with status updates.

Build Items (Claude Code)

| # | Work Item | Effort | Status | Notes |
| --- | --- | --- | --- | --- |
| B1 | /about/ page | — | ✅ DONE | Deployed at /about/. Unlinked from nav. |
| B2 | Nav update: add About link + .active class on ALL pages | 30 min CC | OPEN | Unblocked by B1 completion. |
| B3 | Homepage cross-link to /about/ | 10 min CC | OPEN | Ship with B2. |
| B4 | Executive brief via email (Resend) | 1–2 hrs CC | OPEN | Also adds webhook trigger for I3. Dual-purpose build. |
| B6 | Analytics event tracking | 1–2 hrs CC | OPEN | Scope expanded per I7 — events designed for agent consumption. |
| B7 | Substack CTAs on results page + brief email footer | 30 min CC | BLOCKED on P2 | Campaign doc specifies placement. |

Note: B5 (D1 query endpoint) has been absorbed into I1 (D1 REST API) in Workstream B. The expanded scope serves both workstreams.

Testing

| # | Work Item | Effort | Status | Notes |
| --- | --- | --- | --- | --- |
| T1 | UAT v3 execution (33 test cases, 8 categories) | 3–4 hrs | OPEN | HIGH PRIORITY. All public features depend on this. |
| T2 | Fix Critical/High failures from UAT | 1–3 hrs CC | BLOCKED on T1 |  |

Publish & Launch

| # | Work Item | Effort | Status | Notes |
| --- | --- | --- | --- | --- |
| P1 | LinkedIn 8-post series | 2 hrs/post | DRAFTED | All 8 in linkedin-content.md. Layer 2 agent analyzes engagement post-publish. |
| P2 | Substack launch (The Binding Constraint) | 2–3 hrs | OPEN | 12-step checklist in campaign doc. newsletter.nickjewell.ai domain. |

Documentation & Maintenance

| # | Work Item | Effort | Status | Notes |
| --- | --- | --- | --- | --- |
| D1 | Update NickJewellAI_Project_Status.md | — | ✅ DONE | Completed March 29. |
| D2 | Update CLAUDE.md | — | ✅ DONE | Completed March 29. |
| D3 | Submit sitemap to Google Search Console | 10 min | OPEN | Manual submission accelerates indexing. |
| D4 | Signal log maintenance | 10 min/entry | STARTED | Kevin G. entry done. Ongoing. Migrates to D1 via I2. |
| D5 | Update architecture.md + status doc post-build | 30 min | NEW | Reflects agentic architecture, Python runtime, new D1 tables. |

Low Priority / Future Triggers

| # | Work Item | Effort | Status | Notes |
| --- | --- | --- | --- | --- |
| L1 | Replace About page LinkedIn link with article permalink | 5 min | OPEN | Swap when ‘When AI Should Not Ship’ URL exists. |
| L2 | Industry benchmarking (‘See how you compare’) | TBD | FUTURE | Needs 50+ assessments with industry diversity. |
| L3 | Team assessments (multiple people, same org) | TBD | FUTURE | Enterprise feature. Requires product design. |
| L4 | Payment gate on executive brief | 1 hr CC | FUTURE | Infrastructure exists. Needs volume to justify. |

Note: L5 (score pattern mapping) and L6 (named engagement packages) have been pulled forward into Workstream B as part of I6 (skill file encoding). They are now active dependencies for Layer 2 agents, not future items.

## Workstream B: Data & Intelligence Infrastructure (7 items)

Shared backbone serving both Workstream A and Workstream C. Every hour spent here pays dividends in both. See Agentic Operations Architecture doc for full specifications.

| # | Work Item | Effort | Status | Dependencies |
| --- | --- | --- | --- | --- |
| I1 | D1 REST API (replaces B5). Structured endpoints: /assessments, /signals, /briefs, /drafts. GET + POST + webhook dispatch. | 2–3 hrs CC | NEW | None. Start immediately. |
| I2 | Signal log migration: Excel → D1 table (signal_log) | 1 hr | NEW | I1 (needs REST API for agent access). |
| I3 | Webhook dispatcher: on assessment_complete and email_capture, POST to Python endpoint | 1–2 hrs CC | NEW | I1 (added to API proxy). Python runtime (C1). |
| I4 | Draft queue table in D1 (agent_drafts: pending/approved/sent/rejected) | 30 min | NEW | I1 (table creation via D1 console). |
| I5 | Agent run log table in D1 (agent_runs: type, trigger, status, cost, duration) | 30 min | NEW | I1 (table creation via D1 console). |
| I6 | Skill file encoding: framework docs, outreach templates, tone rules, engagement packages → markdown skills with progressive disclosure | 2–3 hrs | NEW | Engagement packages must be defined (formerly L5/L6). Content exists; restructuring needed. |
| I7 | Analytics instrumentation (expanded B6): events designed for agent consumption with metadata schema | 1–2 hrs CC | NEW | Builds with B6. Same session, expanded scope. |

Key: I1 is the single most important infrastructure item. It serves chat queries (Workstream A), agent data access (Workstream C), and the human-in-the-loop draft queue (Workstream C). Build first.

## Workstream C: Agentic Operations (11 items)

Three capability layers. Built simultaneously, reaching operational readiness at different moments. See Agentic Operations Architecture doc for full specifications, communication patterns, and skill encoding details.

Runtime & Scaffolding

| # | Work Item | Effort | Status | Dependencies |
| --- | --- | --- | --- | --- |
| C1 | Python runtime provisioning: Railway account, GitHub deploy pipeline, env vars (Anthropic key, D1 API URL, Resend key) | 1–2 hrs | NEW | None. Start immediately. |
| C2 | Base agent scaffold: project structure, Anthropic SDK, D1 REST client, Resend client, skill file loader | 2–3 hrs | NEW | C1 (runtime exists). |

Layer 1: Scheduled Automation (Cloudflare Workers on cron)

| # | Work Item | Trigger | Effort | Status | Dependencies |
| --- | --- | --- | --- | --- | --- |
| C3 | D1 morning digest worker | Daily 7 AM ET | 1–2 hrs CC | NEW | I1 (REST API for queries). Resend (exists). |
| C4 | Outreach queue processor | Daily 9 AM ET | 1–2 hrs CC | NEW | I4 (draft queue table). Resend (exists). |
| C5 | Health monitor | Every 6 hrs | 1 hr CC | NEW | None. |
| C6 | Weekly analytics digest | Monday AM | 1–2 hrs CC | NEW | I7 (analytics events deployed). |

Layer 2: Single-Agent Loops (Python on Railway)

| # | Work Item | Trigger | Effort | Status | Dependencies |
| --- | --- | --- | --- | --- | --- |
| C7 | Lead enrichment agent: research company/contact, enrich D1, draft follow-up | Webhook: email_capture | 3–4 hrs | NEW | C2, I1, I3, I4, I6 (outreach skill). |
| C8 | Engagement matcher agent: map scores → engagement package, write recommendation | Webhook: assessment_complete | 2–3 hrs | NEW | C2, I1, I6 (engagement packages skill). |
| C9 | Pattern analysis agent: identify recurring constraint shapes, draft insights | Cron: weekly | 3–4 hrs | NEW | C2, I1, I2 (signal log in D1). |
| C10 | Content drafting agent: draft Substack post from D1 data patterns | Cron: biweekly | 3–4 hrs | NEW | C2, I1, I6 (content style skill). P2 (Substack exists). |

Layer 3: Orchestrated Agent Mesh (deepagents/LangGraph)

| # | Work Item | Trigger | Effort | Status | Dependencies |
| --- | --- | --- | --- | --- | --- |
| C11 | Supervisor pipeline: assessment_complete → parallel sub-agents (enrich + pattern match + engagement match) → assembled follow-up draft | Webhook: assessment_complete + email_capture | 4–6 hrs | NEW | C7, C8, C9 operational. deepagents package validated. |

Note: C11 reuses C7, C8, and C9 as sub-agents under a supervisor. It does not replace them — they continue to run independently for their individual triggers. The supervisor coordinates them in parallel when an assessment completes with an email capture (the highest-signal event).

# Dependency Map

## Workstream A Dependencies

- B2 + B3: Unblocked (B1 done). Ship immediately.

- T1 (UAT): Unblocked. Execute after B2/B3 so About page nav is testable.

- T2: Blocked on T1 results.

- P1 (LinkedIn): Blocked on T1/T2 (publish with confidence). Can start during UAT if no critical issues.

- B4 (Brief email): Independent. Also serves as webhook trigger source for I3.

- B6/I7 (Analytics): Independent. Should be live before P1 drives traffic.

- P2 (Substack): Independent. Unblocks B7.

## Workstream B Dependencies

- I1 (REST API): No blockers. CRITICAL PATH — nearly everything in B and C depends on this.

- I2 (Signal log migration): Depends on I1.

- I3 (Webhook dispatcher): Depends on I1 + C1 (Python endpoint must exist to receive webhooks).

- I4 + I5 (D1 tables): Depends on I1 (created via D1 console, accessed via REST API).

- I6 (Skill encoding): Requires engagement package definition (formerly L5/L6). Content restructuring only.

- I7 (Analytics): Builds with B6. Same session.

## Workstream C Dependencies

- C1 (Python runtime): No blockers. Can start Session 1.

- C2 (Agent scaffold): Depends on C1.

- C3–C6 (Layer 1 workers): Depend on I1 (REST API) and I4 (draft queue). C6 also depends on I7 (analytics events).

- C7–C10 (Layer 2 agents): Depend on C2 (scaffold), I1 (REST API), I3 (webhooks), I6 (skills).

- C11 (Layer 3 supervisor): Depends on C7, C8, C9 being operational. Heaviest dependency chain.

## Critical Path

I1 (REST API) → I3 (webhooks) + I4/I5 (tables) → C7 (first Layer 2 agent) → C11 (Layer 3 supervisor)

This is the longest dependency chain. I1 must be built early. Everything else fans out from it.

# Simultaneous Build Sequence

12 sessions. Three workstreams in parallel. Items grouped by session with cross-workstream economies of scale noted.

## Phase 1: Foundation Sprint (Sessions 1–4)

| Session | Workstream A | Workstream B | Workstream C |
| --- | --- | --- | --- |
| 1 | B2 + B3 (nav + cross-link) | I1 design + begin build (D1 REST API) | C1 (Railway provisioning) |
| 2 | T1 start (UAT execution) | I1 complete + deploy | C2 (agent scaffold) |
| 3 | T1 continue | I2 (signal log → D1) + I4 + I5 (new tables) | C3 (morning digest worker) |
| 4 | T2 (fix Critical/High) | I6 start (skill encoding + engagement packages) | C5 (health monitor) |

Session 2 economy: I1 closes both B5 (Roadmap v2) and I1 (Roadmap v3) in one build.

## Phase 2: Intelligence Sprint (Sessions 5–8)

| Session | Workstream A | Workstream B | Workstream C |
| --- | --- | --- | --- |
| 5 | B4 (brief via email) | I3 (webhook dispatcher — added in same API proxy update as B4) | C4 (outreach queue processor) |
| 6 | B6/I7 (analytics instrumentation) | I6 continue | C7 (lead enrichment agent) |
| 7 | P1 posts 1–2 | I6 complete | C8 (engagement matcher agent) |
| 8 | P1 posts 3–4 | Observability review (first agent runs) | C9 (pattern analysis agent) |

Session 5 economy: B4 (brief email) and I3 (webhook dispatcher) are both API proxy updates. One session, two workstreams served. B4 also becomes the trigger event that activates C7.

## Phase 3: Orchestration Sprint (Sessions 9–12)

| Session | Workstream A | Workstream B | Workstream C |
| --- | --- | --- | --- |
| 9 | P1 posts 5–6 | Cost + quality analysis (first week of agent data) | C10 (content drafting agent) |
| 10 | P2 (Substack launch) | Skill file refinement from agent output | C11 scaffold (supervisor + sub-agent wiring) |
| 11 | B7 (Substack CTAs on site) | D5 (update architecture.md, status, CLAUDE.md) | C11 testing (full pipeline) |
| 12 | P1 posts 7–8 | Documentation complete | C11 production deploy + monitoring |

Session 10 economy: Substack launches (P2) while C10 (content drafting agent) from Session 9 is already producing draft posts. The publication immediately has a content pipeline.

# Decision Points

## Product Triggers

- After UAT v3 (T1): Systemic issues or edge cases? Determines P1 start safety.

- After 10 assessments with enrichment: Is D1 data clean? Are enriched records better than un-enriched?

- After 25 assessments: LinkedIn data post viable (‘What the first 25 Jewell Assessments revealed’).

- After 50 assessments: Industry benchmarking viable. Payment gate consideration. Substack data posts.

## Agentic Triggers

- After 5 agent runs: Is output quality sufficient? Minimal editing = proceed. Heavy editing = refine skills and prompts first.

- After 25 enriched assessments: Is engagement package matching >80% accurate? If not, more signal log data needed.

- First engagement closed via pipeline: Write case study. Double down on highest-signal touchpoint.

- Agent cost exceeds $100/mo: Review ROI. At current pricing, extremely unlikely to be a constraint.

- 50+ leads/week: Digest-based review becomes bottleneck. Build approval UI.

- Layer 3 sub-agent failure >10%: Add retry logic, fallback to Layer 2, consecutive failure alerting.

## Architecture Triggers

- D1 hits free tier limits (5M reads/day): Evaluate Cloudflare D1 paid tier ($0.75/million). Unlikely at current scale.

- Railway hobby tier insufficient: Upgrade to Pro ($20/mo) or evaluate Fly.io migration.

- deepagents breaking change: Pin package version. Test upgrades in staging.

- Need for real-time agent execution (not cron/webhook): Evaluate persistent WebSocket connection or SSE from Railway to browser.

# Effort Summary

| Workstream | Open Items | Estimated Hours | Sessions Span |
| --- | --- | --- | --- |
| A: Product & Content | 13 items (4 done, 9 active) | 25–35 hrs | All 12 |
| B: Data & Intelligence Infrastructure | 7 items (all new) | 10–15 hrs | Sessions 1–8 (concentrated) |
| C: Agentic Operations | 11 items (all new) | 20–30 hrs | Sessions 1–12 (progressive) |
| Total | 31 open items | 55–80 hrs | 12 sessions (~5–7 hrs each) |

At the current daily session pace, approximately 3–4 weeks to full operational capability. Layer 1 workers running by Session 4. First Layer 2 agent online by Session 6. Layer 3 orchestration targets Session 12.

# Monthly Infrastructure Cost (at full capability)

| Item | Cost |
| --- | --- |
| Cloudflare Pages + Workers + D1 | $0 (free tier) |
| Resend (transactional email) | $0 (free tier, 3K emails/mo) |
| Railway (Python runtime) | $5/mo |
| Anthropic API (assessments + agents, ~30/mo) | $5–15/mo |
| Total | $10–20/month all-in |

# Explicitly Removed from Scope

- MCP server project (mcp-vendor-intel) — secondary project, not on active roadmap.

- Job search / interview narrative work — paused. Portfolio is the job search.

- A/B testing infrastructure — premature optimization at current volume.

- CMS for content publishing — static HTML is correct for current scale.

- Approval UI for agent drafts — future trigger at 50+ leads/week. Digest-based review is sufficient now.

Roadmap v3  |  March 30, 2026  |  Next review: after Session 4 (Phase 1 complete)