NICKJEWELL.AI

Full Project Roadmap & Priority Matrix

Updated March 29, 2026  |  Audited across all project docs and conversation history

# What's Built & Deployed

Homepage with thesis, pattern section, framework preview, logo section, writing, contact. Framework page with 5-layer deep dive, company stories, transitions, sticky layer nav, assessment backlinks. Assessment engine with 3-tier adaptive flow, API integration (Sonnet 4 + Opus 4.6), streaming executive brief, contact form gate, deterministic fallback. 5 standalone writing pages with SEO and inline CTAs. Save Results email pipeline via Resend. nick@nickjewell.ai (send + receive). OG images for all 3 pages. Full accessibility overhaul (WCAG AA). SEO infrastructure (sitemap, robots, structured data, favicon). D1 auto-capturing all assessments with enriched Pulse fields. Admin bypass for rate limiting. www redirect. Framework sticky layer nav (resolved after multiple scroll-margin fixes).

# All Open Items (17 total)

## Build Items (Claude Code sessions)

| # | Work Item | Effort | Why It Matters | Status |
| --- | --- | --- | --- | --- |
| B1 | /about/ page (full reference doc + copy ready, 9 UAT cases written) | 2-3 hrs CC | Credibility page. People Google you before responding. | OPEN |
| B2 | Nav update on ALL pages to add About link + .active class | 30 min CC | Blocked on B1. UAT v3 TC-15 tests this. | BLOCKED |
| B3 | Cross-link from homepage contact section to /about/ | 10 min CC | About Page Reference doc: 'Built by a practitioner, not a vendor' CTA | BLOCKED |
| B4 | Executive brief delivered via email (Resend) | 1-2 hrs CC | Brief currently streams in-browser only. Vanishes on tab close. | OPEN |
| B5 | D1 query endpoint (functions/d1-query.js) | 30 min CC | Conversational access to assessment data from this chat. | OPEN |
| B6 | Analytics event tracking (Cloudflare Web Analytics) | 1 hr | Custom events: assessment_start, tier_complete, assessment_complete, brief_email_submit | OPEN |
| B7 | Substack CTAs on assessment results page + brief email footer | 30 min CC | Blocked on Substack launch. Campaign doc specifies placement. | BLOCKED |

## Testing

| # | Work Item | Effort | Why It Matters | Status |
| --- | --- | --- | --- | --- |
| T1 | UAT v3 execution (33 test cases, 8 categories) | 3-4 hrs | Every public feature depends on this. HIGH PRIORITY. | OPEN |
| T2 | Fix any Critical/High failures from UAT | 1-3 hrs CC | Blocked on T1 results. | BLOCKED |

## Publish & Launch

| # | Work Item | Effort | Why It Matters | Status |
| --- | --- | --- | --- | --- |
| P1 | LinkedIn 8-post series (begin publishing) | 2 hrs/post | Primary traffic driver. All 8 drafted in linkedin-content.md. | DRAFTED |
| P2 | Substack launch (The Binding Constraint) | 2-3 hrs setup | 12-step technical checklist in campaign doc. newsletter.nickjewell.ai domain. | OPEN |

## Documentation & Maintenance

| # | Work Item | Effort | Why It Matters | Status |
| --- | --- | --- | --- | --- |
| D1 | Update NickJewellAI_Project_Status.md | 30 min | Current version is stale vs. deployed state. HIGH-MED priority. | OPEN |
| D2 | Update CLAUDE.md before about page build session | 15 min | Claude Code reads this first. Needs current state for context. | OPEN |
| D3 | Submit sitemap to Google Search Console | 10 min | Mentioned in content strategy. Manual submission accelerates indexing. | OPEN |
| D4 | Signal log maintenance (add every tester/conversation) | 10 min/entry | Kevin entry done. Ongoing as people engage. | STARTED |

## Low Priority / Future Triggers

| # | Work Item | Effort | Why It Matters | Status |
| --- | --- | --- | --- | --- |
| L1 | Replace About page LinkedIn link with 'When AI Should Not Ship' permalink | 5 min | About Page Reference doc: swap when article URL exists. | OPEN |
| L2 | Industry benchmarking ('See how you compare') | TBD | Needs 50+ assessments with industry diversity. | FUTURE |
| L3 | Team assessments (multiple people, same org) | TBD | Enterprise feature. Requires product design. | FUTURE |
| L4 | Payment gate on executive brief | 1 hr CC | Infrastructure exists. Needs volume to justify. | FUTURE |
| L5 | Map D1 score patterns to engagement types | 2-3 hrs | Needs 20+ assessments. Signal log feeds this. | FUTURE |
| L6 | Named engagement packages in brief recommendations | TBD | Assessment becomes a sales conversation. | FUTURE |

# Dependency Map

Understanding what blocks what:

B1 (About page) → unblocks B2 (nav update) → unblocks B3 (cross-link) → unblocks T1 Category 8 (About page UAT cases)

T1 (UAT v3) → unblocks T2 (fixes) → unblocks P1 (LinkedIn publishing with confidence)

P2 (Substack launch) → unblocks B7 (Substack CTAs on site)

D2 (CLAUDE.md update) → should happen BEFORE B1 (About page build session)

B5 (D1 endpoint) → independent, no blockers, enables ongoing data analysis

B4 (Brief via email) → independent, no blockers, uses existing Resend pipeline

B6 (Analytics) → independent, should be live before LinkedIn publishing drives traffic

# Recommended Sequence

Based on your 30-60 minute daily sessions and the dependency map:

## Phase 1: About Page + Docs (Sessions 1-4)

Session 1: Update CLAUDE.md and NickJewellAI_Project_Status.md to reflect current deployed state. (D1, D2)

Session 2-3: Build /about/ page in Claude Code using About Page Reference doc. (B1)

Session 4: Nav update across all pages + homepage cross-link to /about/. Submit sitemap to Search Console. (B2, B3, D3)

## Phase 2: Validate (Sessions 5-7)

Session 5-6: Run UAT v3 (33 test cases across 8 categories including new About page cases). (T1)

Session 7: Fix any Critical/High failures. (T2)

## Phase 3: Infrastructure (Sessions 8-10)

Session 8: Build D1 query endpoint. (B5)

Session 9: Build executive brief email delivery via Resend. (B4)

Session 10: Enable Cloudflare Web Analytics + custom events. (B6)

## Phase 4: Go to Market (Sessions 11+)

Sessions 11-18: Publish LinkedIn posts 1-8 (one every 2 days). Log signal from every response. (P1, D4)

When ready: Substack launch + wire CTAs onto site. (P2, B7)

# Decision Points

After UAT v3: Are there systemic issues or just edge cases? Determines whether LinkedIn publishing is safe to start.

After 10 assessments: Is D1 data clean? Are enriched Pulse fields populating? First data quality check.

After 25 assessments: Enough for a LinkedIn post with real aggregate data ('What the first 25 Jewell Assessments revealed').

After 5 signal log entries: Review for engagement shape patterns. Same layer gaps recurring across industries?

After 50 assessments: Industry benchmarking viable. Consider payment gate. Substack data posts become possible.

# Explicitly Removed from Scope

MCP server project (mcp-vendor-intel) — secondary project, not on active roadmap.

Job search / interview narrative work (curriculum Days 51-54) — paused.

A/B testing infrastructure — premature optimization at current volume.

CMS for content publishing — static HTML is correct for current scale.